## Slide 1: Digital POWRR Project Timeline DRAFT – June 2013
Campus Interviews
Test Data Collection
Software Requisition
Technology Installation
Tool Grid
Case Study Creation
System Testing
Full Initial Draft Editing
IMLS Editing Final Report
Dissemination
Jul/Aug
Sep/Oct
Nov/Dec
Jan/Feb
Mar/Apr
May/Jun
Jul/Aug
Sep/Oct
Nov/Dec
Jan/Feb
Mar/Apr
May/Jun
Advisory Board Meeting
Conference Presentation
A
A
A
A
2012
2014
Partner Face 2 Face
P
P
P
2013
Jul/Aug
Sep/Oct
Nov/Dec
A
P