## Slide 1: Digital POWRR Project Timeline DRAFT – December 2012
Campus Interviews
Test Data Collection
Software Requisition/ Vendor Negotiation
Technology Installation
Tool Grid
Case Study Creation
System Testing
Full Initial Draft Editing
IMLS Editing Final Report Due
Jul/Aug
Sep/Oct
Nov/Dec
Jan/Feb
Mar/Apr
May/Jun
Jul/Aug
Sep/Oct
Nov/Dec
Jan/Feb
Mar/Apr
May/Jun
Advisory Board Meeting
National Conference at NIU
Conference Presentation
A
A
A
A
A
2012
2014
Partner Face 2 Face
P
P
P